Request for Proposals

| RFP: Procurement Programming – Spend Analysis & Program Development | Proposal Due By: March 25, 2026 at 5pm CT | Entrepreneurship Center for Growth and Excellence |
| --- | --- | --- |
| Project Overview: We seek proposals from qualified vendors to conduct a spend analysis and develop a procurement program aimed at increasing procurement opportunities for local businesses with anchor institutions and/or large businesses in Birmingham, Alabama. This initiative is part of a broader effort to promote the growth of and build the capacity of local businesses. The vendor will conduct the foundational analysis of enterprise-level procurement data, uncover opportunities for increasing local spending, and design a community-informed strategy for sustaining the work into the future. Interested vendors must demonstrate: - Experience in advancing procurement practices and capacity building for local businesses. - Proven track record for categorizing spend by category across companies. - Proven track record in project management and stakeholder engagement. - Strong analytical and reporting capabilities. - Ability to develop and implement effective fundraising strategies for program sustainability. |  |  |
| Project Goals: - Deliver a plan for the development of a sustainable and impactful procurement program that engages local stakeholders, determines which businesses’ spend should be assessed, recruits the business participants, includes a SWOT analysis of the local procurement landscape, defines decision-making processes, and includes a long-term funding strategy. - Conduct a spend analysis to set benchmarks and goals, track outreach and procurement opportunities, engage supplier and business support organizations, and develop a plan for navigating corporate networks. - Create pathways for more local businesses to obtain multi-year contracts and identify business types that with proper development can be ready for contracts. |  |  |
| Scope of Work: - The successful respondent will develop a best-in-class procurement program that leads to: - increased engagement of large businesses in Birmingham with smaller Birmingham businesses, - increased multi-year contracts for smaller businesses, - stronger procurement practices, - development of businesses to have increased capacity to obtain contracts, - growth of existing businesses by revenue generated and number of employees, and - collaboration with businesses and opportunities in other markets. - The successful response will include: - clear timeline and approach - how success will be measured - clear goals for increases in revenue and job creation - track record of previous success with a similar effort - references who can speak to respondent’s ability to execute |  |  |
| Current Roadblocks and Barriers to Success - Generating buy-in from large businesses who may perceive no imperative to deviate from existing behavior. - Challenges identifying small businesses that are ready for the procurement opportunities. |  |  |
| Evaluation Metrics and Criteria - Delivery of a comprehensive plan for procurement including determination of which large companies should participate in the effort, a spend analysis, SWOT, and plan for stakeholder engagement. - Establishment of data-informed goals and metrics tracking systems. - Program design that leads to increase in revenue and creation of jobs at clearly identifiable small businesses. - Demonstration of proven track record of previous success with a similar effort. |  |  |
| Submission Requirements - Company profile, relevant experience, and current staffing structure. - Outline in detail your proposed process, timeline, staffing needs, impact measurement, detailed scope of work, and success record for undertaking similar projects. - Itemized budget of planned and actual funds distribution. |  |  |
| Project Outcomes Due By: December 1, 2026. Project outcomes include delivery of the completed spend analysis, SWOT, plan for stakeholder engagement, data-informed goals and metrics tracking system, designed program that responds to the analysis, funding plan for ongoing sustainability of the effort. |  | Max Budget: $200,000 |
| Contact: Kendra Key | Email for Submission: connect@ecbham.com Subject: Procurement RFP | Phone # for specific questions: 205-847-5474 |